## Sheet1
Risk Assessment for Return to Work following Coronavirus | Phase 1
The Prepare, Inform, Prevent, Recover Approach
Guidance using the Prepare, Inform, Prevent, Recover (PIPR) approach. | Stage 1
Prepare: | Notes:
Get ready to return to work and identify your return to work plan. This should include the following:
Leadership team discuss and agree the business return to work programme | Phase 1 agreed - await government advice to launch
Plan to prepare your building for occupancy | Plan completed suject to new government guidelines. Phase 1 is session based on 2 days per week. Markings to be implemented. Staff to receive early briefing 1st May 2020.
Arrange to conduct a preoccupancy inspection and arrange a pre-occupancy deep cleaning program | Pre-inspection to be completed by 15 May 2020. Cleaning to be undertaken once date Phase 1 known.
Train your teams on good hygiene matters and establish a daily cleaning schedule | Staff to bring own cleaning products (paid by the company) and clean own space as they leave. Cleaner to attend outside staff days.
Review any service which may present a health issue and establish how you can minimise risk | N/A
Test all emergency and life safety systems | Fire alarm to be tested at first session during Phase 1. Security as before.
Agree who will return to work and consider the following:
Workplace distancing and space availability | Maring to be in place inside and outside. Conference rooms to be marked up. Only 1 person per work station during Phase 1. Kitchen off limits. Toilets converted to dual sex use and 1 person system to be implemented.
Work routines to achieve workplace distancing | Phase 1 has limited sessions. Shorter intense sessions. No car shareing.
Vulnerable or at risk staff | RA completed in March 2020. Remain at home during Phase 1.
Staff who have child or care responsibilities | Notice of sessions to be given. Short intense sessions during Phase 1 Attend remotely if cannot make other arrangements.
Travel arrangements to, where possible, reduce the need for public transport | Staff to speak with line manager.
Establish workspace distancing protocols based on Government advice. This should be considered for the following:
Staggered arrival and departure | To be in place plus external markings.
Building entrance and/or exit protocols | See above plus posters on arrival. Staff to wash hands on arrival. Staggered exits
Workspace | During Phase 1 only 1 per bank of desks. Staff to clean personal space on exit.
Pantries and any space where food is prepared and eaten | Kitchen off limits. Staff to bring personal food and drinks. Short, intensive sessions.
Meetings internal | Social distance rules to apply
Meetings with clients | N/A during Phase 1
Security and Emergency arrangements | As normal
You also need to consider the consequences of increased anxiety | Links to mental health webinars and tools circulated throughout lockdown. Discuss on a 1:1
And importantly, establish a protocol to respond to expected spikes in the outbreak. This will ensure a quick response if you need to send your team home, you can do this effectively without disruption to service. | This is for Phase 1 only and will be adapted as government guidelines change.
Inform:
Establish a return to work program and establish who will communicate with staff. The more senior the person, the better.
Arrange a welcome back to work program for staff and managers, to inform them of the ‘new’ workplace protocols. This includes:
Workplace distancing protocol and building cleaning arrangements | Staff to be shown RA 1st May 2020. Photos of markings to be sent. Cleaner to attend once Phase 1 begins. Only 1 staff per bank of desks and conference rooms to be clearly marked.
Travel and arrival arrangements
This is particularly important for those who cycle to work or use changing facilities | No car shareing. Shower facilities available as usual.
Relaxation of car share program, if in place | N/A
Follow Government advice on use of public transport | To be reinforced once Phase 1 begins and latest guidelines known.
Working arrangements including breaks | Short, intense sessions during Phase 1. No need for linch break.
Seating arrangements | Only 1 person per bank of desks. Conference rooms clearly marked.
Workstation health and hygiene requirements | Kitchen off limits. Each person to wipe down person space on exit. Last person to leave wipe down door handles on leaving.
Eating and drinking and use of fridges for personal food | N/A in Phase 1 - kitchen off limits
Ill-health reporting and staff support program | Usual absence reporting. Staff feeling ill should not attend during Phase 1.
End of day protocols, where an alternative team may be working on site | N/A Only 1 session per day
Travel to and from client sites or meetings | N/A
Vehicle hygiene requirements and checks | N/A
And keep reinforcing your health and hygiene messages as ultimately, they will keep people healthy and safe. | Weekly updates
Prevent:
Ensure that health and hygiene is managed and maintained by:
Identifying key touch points in the workplace and providing appropriate sanitation stations to allow hands to be cleaned | In place
Washroom cleanliness | Only 1 person at any time. Cleaner to be in place.
Determining cleaning frequencies which need to consider an initial clean of surfaces and HVAC system | To be in place prior to Phase 1
Cleaning to consider core activities and staff provided with appropriate PPE and be visible to staff during the working day | To be considered against latest government guidelines prior to Phase 1
PPE is recommended for psychological control, rather than a safety measure
Reviewing:
Food preparation and server areas to ensure workspace distancing can be maintained | Kitchen off limits.
Deliveries | N/A
Waste Arrangements included specific arrangements for PPE worn by cleaners and FM Staff | As normal
Cycle to work arrangements and changing facilities where provided | As normal
Reinforcement of workplace distancing protocols | Posters to be displayed. Marking to be undertaken.
Recover:
The business recovery is a key stage. Leaders should monitor the effectiveness of the return to work program to ensure that it remains effective and is supporting those who have returned to work. It can also be used to restore confidence in the business.
Review lessons learnt from the outbreak and ask for feedback. Critique what you’ve learnt and use this to improve. | Questionnaire issued April 2020 - no issues raised to date. Review Phase 1 before proceeding to Phase 2. Maintain attendance at online information sessions.
Review and update your Business Continuity Plan. Most organisations will have had their plan activated by the outbreak so we would encourage you to learn from this. | Business Continuity Plan reviewed April 2020 - continual update during 2020
Finally, review what you’ve learnt from the period of time people have been working from home. Are there positives to be had? We believe that lockdown has reconnected families and given people time look at what’s important to them, so it might be time to look at how teams work in a different way! | Review at end of each Phase. Consideration to new ways of working built into questionnaire - to be completed at final end of lockdown.